## Slide 2
An improved cleanroom will facilitate our acceleration to a new level of testing/capacity/quality/market share
Acceleration
Increase our competitiveness
Increase our appeal to customers
Appeal to new customers
We have defined where we are headed- what do we want to take us there? What can we afford? Timeframe? What strategy will maximize our capabilities/opportunities?

## Slide 3: Objectives for this meeting:
Present multiple options and information regarding the product sterility cleanrooms
Provide a recommendation for a final decision
Determine what additional questions must be addressed before a final decision can be made and approved
Consider the various departments/functions that will be impacted by these decisions, and involve those areas as early as possible

## Slide 4: The assignment:
What we have been doing for the last few weeks? – Dec to Jan
Weekly meetings
Evaluating/coordinating short term fixes prior to TGA – painting/patching/fixes
Price quotes
Evaluating needs/growth potential/capacity
Researching alternative solutions
Evaluating leasing options
Structural evaluation of RW2 – bad news…
Preliminary evaluation/discussion of options
Meeting with contractors- multiple vendors for each option
Evaluating areas and functions that will be impacted by short term and long term decisions

## Slide 5: Three options
Option 1 – more frequent repairs; no changes
Option 2 – wall panels + new floors
Option 3 – new cleanroom
Note: expanding cleanroom within current area of RW2 was determined to not be an option based on structural evaluation

## Slide 6: Option 1
Increase frequency of repair/maintenance events
Actual age of cleanroom (2001-2002)
Repair/resurface the floor 2015
3 – 4 times/year
Shutdown/revalidation as necessary
Risk: TAT surrounding shutdowns, quality, inspections, requalification risks,
Period/duration: not sure, how long this will be sustainable (1 year - ______?)

## Slide 7: Option 2
Rework current space – use of wall panels and resurface floors
Cost - $300,000
Cost varies dependent on number of events
Options for longterm use of retrofitted space:
    BI sterility
    Redundancy for sterility testing
Timeframe – next slide
Potential materials – Altro whiterock, Crayne composite glassboard (samples)
Multiple options for contractors: refer to contact list
DURATION: dependent on space, not materials
3 – 5 years (based on projected growth)
RISK: impact from shutdowns, age of air handlers (12-13 years)

## Slide 8: Timeframe for option 2
1 shutdown = 18 days
2 shutdowns = (slightly lower cost/faster)
7/8 days for wall paneling + some flooring
7/8 days for remaining wall paneling & flooring
3 shutdowns = (300,000) Recommendation
7/8 days for paneling + painting
6/7 days for remaining paneling & some flooring
6/7 days for remaining flooring

## Slide 9
Vendor Name | Address | Phone | Contact | Email | Website
DAW Technologies | 1600 West 2200 South Suite 201 SLC, UT 84119 | 801-554-2977 / 801 -977-3100 | Brad Jones | BJones@dawtech.com | www.dawtech.com
Hodess Construction Corporation | 100 John L Dietsch Sq. Attleboro Falls, MA 02763 | 508-695-1012 | Jason Dollarhide | dollarhide@hodess.com | www.hodess.com
Pacific Environmental Technologies, Inc. | 135 Enterprise Court Corona, CA 92882 | 951-582-9948 | Brandon Bunch | brandonb@peticleanair.com | www.peticleanair.com
Clean Rooms West, Inc. | 1392 Industrial Drive Tustin, CA 927780 | 800-772-6634 / 714-258-7700 | Kelly Barton | kelly@cleanroomswest.com | www.cleanroomswest.com
Lasco Services | 601 Compton Irving, TX 75061 | 800-815-2726 / 972-513-1875 |  | sales@lascoservices.com | www.lascoservices.com

## Slide 10
G-con – new cleanroom builds
Benchmark – thermofisher/hyclone cleanrooms

## Slide 11: Option 3
Forego option 2; expedite a new build
Lease a space – limited options/high prices
Build a clean space – modular cleanroom
Potential cost of 3M ;
Timeframe – just a few months for construction after a space is identified and plans are created
Most contractors from previous list are options for a new build as well: Hodess, G-Con, etc.
Risk – price point, time frame

## Slide 12: Proposal from the “cleanroom committee”
Option 2 – retrofit the cleanroom with panels + resurface floor – (start July 2015)
Then Option 3
– Strategically plan expansion options/location
–New cleanroom (3-5 years)

## Slide 13: input/considerations/questions
Metrology
Quality
Sales
Accounting
Validations
Management
Senior leadership team

## Slide 14: Next steps/goals:
Refine quotes/timelines
What other information is needed prior to making a decision?
Refine deadline for the next step?
What is the deadline for customer notification?
When/how do we notify customers?
Visit cleanrooms with panels/modular materials – gain perspective of materials from those who have implemented them
Additional training/research for cleanroom design and management – conference in boston; cleanroom microbiology book – 600 pages; webinars; Other resources
Bring in additional contractors for evaluation/consultation

## Slide 15
200,000 – 300,000 for 3 – 5 years
4 days minimum labor for floors (not counting cure time)
Walls first; then floors
Hoods will have to be moved when floors are done. Requalification of all hoods ~ 1 day; work can begin in one hood while others are being requalified
Evaluate new hoods
New floors are a must/regardless of other decisions
Structural analysis of RW2 – will not support expansion of current Cleanroom
RW3 could support a new cleanroom; RW1/2 ground floor restructure?
< 1 year options (paneling):
1 – 18 day shutdown for everything (walls, floors, requalification
2 – 2 shutdowns; 4 – 5 days for wall panels, 6 – 7 days floors + hood requal
3 – 3 shutdowns 4 – 5 days each, wall panels then a portion of the floors, then the remaining floors
After new cleanrooms are built, old cleanrooms may be used for redundancy + BI sterility cleanrooms
Provide contact info for each of the options
Actual age of the cleanroom

## Slide 16
FRP panels – static issues? Flat finish available or only reflective?
Repair of panels –
Square footage of current area?
Stats – 5 testing suites, area for media/sample storage, gowning area, sterilizers
Cost for panels; new cleaning plan to be evaluated – less clorox?
More extensive maintenance program?
Lease a clean space, building a new facility – modular
Is a clean space available?
3 proposals/options + recommendation
New clients/projects – short term potential for growth: more MTF, wedgewood pharm, fresenius detention, medline glove testing, constraints have not been expertise; only resources/facilities